## Sheet1
Defect ID | Detected in Cycle | Build Sequence | Test Phase | Detected in Release | Detected on Date | Detected By | Assigned To | Actual Fix Time (Hrs) | Business/Functionality | Closing Date | Description | Environment | Modified | Priority | Reason Code | Reproducible | Request Type | Severity | Status | Summary
1 | Cycle 1 | UN_01 | System Testing | Release | 2021-09-07 | Sivaranjani |  | 2 | UN_AddOption | 2021-09-08 | Option value name is inappropriate | QA |  | High | Coding Errors | Y | Defect | High | Closed | once the new Options are added to the lists, the Option name is visible whereas the value name is not updated as it is a required field, ie it has no functionality but it is mandatory
2 | Cycle 1 | UN_02 | System Testing | Release | 2021-09-07 | Sivaranjani |  | 2 | UN_AddOption | 2021-09-08 | Sort Order under Option values is not suitable | QA |  | High | Coding Errors | Y | Defect | High | Closed | During the addition of new Options, there are 2 Sort order fields to be filled,