## Sheet1
Defect ID | Detected in Cycle | Build Sequence | Test Phase | Detected in Release | Detected on Date | Detected By | Assigned To | Actual Fix Time (Hrs) | Business/Functionality | Closing Date | Description | Environment | Modified | Priority | Reason Code | Reproducible | Request Type | Severity | Status | Summary
1 | Cycle 2 | UN_01 | System Testing | Release | 2021-09-07 | Sivaranjani |  | 2 | UniformStore_Admin_Options | 2021-09-08 | Type field should be mandatory | QA |  | Medium | Coding Errors | Y | Defect | medium | Closed | While adding the new options, the type should be made mandatory
2 | Cycle 2 | UN_02 | System Testing | Release | 2021-09-07 | Sivaranjani |  | 2 | UniformStore_Admin_Options | 2021-09-08 | Date, time and file under type field is not necessary | QA |  | Medium | Coding Errors | Y | Defect | medium | Closed | date, time and files are not needed under type field in measurement units.